## Gantt planification
Marketing Plan Template
Teresa Canive
2019-11-08 11:37
|  | November 2019 | [14 empty] | December 2019 | [21 empty] | January 2020 | [22 empty] | February 2020
 | time axis 2019-11-11 to 2020-02-07
Project activities | Status | time axis 2019-11-11 to 2020-02-07
External Analysis | done | bar: 2019-11-11 to 2019-11-19
Client Meeting 1 | done
Client Meeting 2 | todo | bar: 2019-11-18 to 2019-11-19
Survey | todo
Internal Analysis | todo | bar: 2019-11-20 to 2019-12-02
Estimated Goals | todo
Define strategy | todo | bar: 2019-12-05 to 2019-12-09
Optimize Media Plan | todo
Survey Results Analysis | todo | bar: 2019-12-10 to 2019-12-20
Budget and ROI | todo
Table for control indicators | todo | bar: 2019-12-26 to 2019-12-30
Scenario Planning | todo
Client Meeting 3 | todo | bar: 2020-01-03 to 2020-01-06
Materials development | todo | bar: 2019-11-12 to 2020-01-06; 2020-01-23 to 2020-02-07
Delivery | todo | bar: 2020-01-23 to 2020-01-24

## Project overview
Marketing Plan Template
Teresa Canive
2019-11-08 11:37
Project team | Role
Teresa Canive | Project owner
Patricia Parra | Team member
Jonas Jonas | Team member
Activity | Involved | Goals |  | Subtasks | Assigned to | Date | Time
External Analysis (66% Completed)
11 Nov 2019 - 19 Nov 2019 (7 days) | Teresa Canive | No goals | - | Market
| Patricia Parra |  | ✓ | Competitors
|  |  | ✓ | FODA
Client Meeting 1
11 Nov 2019 - 15 Nov 2019 (5 days) | Patricia Parra | No goals |  | No subtasks
Client Meeting 2
18 Nov 2019 - 19 Nov 2019 (2 days) | Teresa Canive | No goals |  | No subtasks
Survey
18 Nov 2019 - 9 Dec 2019 (16 days) | Teresa Canive | No goals |  | No subtasks
Patricia Parra
Internal Analysis (0% Completed)
20 Nov 2019 - 2 Dec 2019 (9 days) | Jonas Jonas (jonasjj) | No goals | - | Target
| Patricia Parra |  | - | Customer Journey
|  |  | - | Current Strategy
Estimated Goals (0% Completed)
3 Dec 2019 - 4 Dec 2019 (2 days) | Patricia Parra | No goals | - | Crear cuenta |  | 1 May 2019 | 01:00
Define strategy
5 Dec 2019 - 9 Dec 2019 (3 days) | Teresa Canive | No goals |  | No subtasks
Optimize Media Plan (50% Completed)
10 Dec 2019 - 20 Dec 2019 (9 days) | Teresa Canive | No goals | ✓ | Define campaigns
| Patricia Parra |  | - | Rate research
Survey Results Analysis
10 Dec 2019 - 20 Dec 2019 (9 days) | Teresa Canive | No goals |  | No subtasks
Budget and ROI
23 Dec 2019 - 25 Dec 2019 (3 days) | Patricia Parra | No goals |  | No subtasks
Table for control indicators
26 Dec 2019 - 30 Dec 2019 (3 days) | Patricia Parra | No goals |  | No subtasks
Scenario Planning
31 Dec 2019 - 2 Jan 2020 (3 days) |  | No goals |  | No subtasks
Client Meeting 3
3 Jan 2020 - 6 Jan 2020 (2 days) |  | No goals |  | No subtasks
Materials development
7 Jan 2020 - 22 Jan 2020 (12 days) |  | No goals |  | No subtasks
Delivery
23 Jan 2020 - 24 Jan 2020 (2 days) |  | No goals |  | No subtasks