## Gantt planification
Marketing Plan
Teresa Canive
2018-02-22 11:34
|  | February 2018 | [7 empty] | March 2018
|  | 2018-02-19 | 2018-02-20 | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30
Project activities | Status | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Design Objetives | done | bar: 2018-02-20 to 2018-03-14
Congress | done
Draft | done
Delivery | todo
Meeting | done | bar: 2018-03-09
Design Context | todo
Analysis | todo
Presentation | todo
Analysis taget | todo | bar: 2018-03-22 to 2018-03-23
Meeting2 | todo | bar: 2018-02-19; 2018-02-21; 2018-02-23 to 2018-03-21; 2018-03-26 to 2018-03-30

## Project overview
Marketing Plan
Teresa Canive
2018-02-22 11:34
Project team | Role
Teresa Canive (teresacam) | Project owner
Richard Balet (richard) | Project manager
Activity | Involved |  | Goals |  | Subtasks
Design Objetives
20 Feb 2018 - 14 Mar 2018 (17 days) | Richard Balet (richard) | ✓ | Review the plan | ✓ | <span id="result_box" class="short_text" lang="en"><span class="">Determine the subject</span></span>
| Teresa Canive (teresacam) | - | Analysis of data | - | Meeting
|  |  |  | - | <span id="result_box" class="short_text" lang="en"><span class="">Draft</span></span>
Congress
23 Feb 2018 - 23 Feb 2018 (1 days) |  |  | No goals |  | No subtasks
Draft
26 Feb 2018 - 2 Mar 2018 (5 days) |  |  | No goals |  | No subtasks
Delivery
9 Mar 2018 - 12 Mar 2018 (2 days) |  |  | No goals |  | No subtasks
Meeting
9 Mar 2018 - 9 Mar 2018 (1 days) |  |  | No goals |  | No subtasks
Design Context
15 Mar 2018 - 20 Mar 2018 (4 days) | Richard Balet (richard) | - | Test 01 | ✓ | Analysis 1
| Teresa Canive (teresacam) | - | Overview | ✓ | Suppliers
|  | ✓ | First Draft | ✓ | Subtask
|  |  |  | - | Analysis 2
Analysis
15 Mar 2018 - 16 Mar 2018 (2 days) |  |  | No goals | - | Drafts
Presentation
21 Mar 2018 - 21 Mar 2018 (1 days) |  | ✓ | Results test |  | No subtasks
|  | - | Make a decision
Analysis taget
22 Mar 2018 - 23 Mar 2018 (2 days) |  |  | No goals |  | No subtasks
Meeting2
22 Mar 2018 - 23 Mar 2018 (2 days) |  |  | No goals |  | No subtasks