## Gantt planification
Implementation 07
Teresa Canive
2019-01-30 15:08
|  | March 2019 | [19 empty] | April 2019 | [21 empty] | May 2019
 | time axis 2019-03-04 to 2019-05-17
Project activities | Status | time axis 2019-03-04 to 2019-05-17
Define goals | todo | bar: 2019-03-04 to 2019-03-07
Kick-off Meeting - fase 1 | todo
Open Questions | todo | bar: 2019-03-13 to 2019-03-19
Analysis data | todo
Team meeting | todo | bar: 2019-03-21 to 2019-03-22
Plan a draft of your strategy | todo
Team meeting 2 | todo | bar: 2019-04-01 to 2019-04-02
Re-planning | todo
Deadline 1st goals | todo | bar: 2019-04-08 to 2019-04-09
Define goals fase 2 | todo
Kick off meeting Fase 2 | todo | bar: 2019-04-15 to 2019-04-16
Open Questions fase 2 | todo
Analysis data fase 2 | todo | bar: 2019-04-24 to 2019-05-03
Team meeting Fase 2 | todo
Plan a draft of your strategy Fase 2 | todo | bar: 2019-04-29 to 2019-05-01

## Project overview
Implementation 07
Teresa Canive
2019-01-30 15:08
Project team | Role
Teresa Canive (tere) | Project owner
Activity | Involved | Goals | Subtasks | Assigned to | Date | Time
Define goals
4 Mar 2019 - 7 Mar 2019 (4 days) |  | No goals | No subtasks
Kick-off Meeting - fase 1
8 Mar 2019 - 12 Mar 2019 (3 days) |  | No goals | No subtasks
Open Questions
13 Mar 2019 - 19 Mar 2019 (5 days) |  | No goals | No subtasks
Analysis data
20 Mar 2019 - 29 Mar 2019 (8 days) |  | No goals | No subtasks
Team meeting
21 Mar 2019 - 22 Mar 2019 (2 days) |  | No goals | No subtasks
Plan a draft of your strategy
25 Mar 2019 - 27 Mar 2019 (3 days) |  | No goals | No subtasks
Team meeting 2
1 Apr 2019 - 2 Apr 2019 (2 days) |  | No goals | No subtasks
Re-planning
3 Apr 2019 - 5 Apr 2019 (3 days) |  | No goals | No subtasks
Deadline 1st goals
8 Apr 2019 - 9 Apr 2019 (2 days) |  | No goals | No subtasks
Define goals fase 2
10 Apr 2019 - 12 Apr 2019 (3 days) |  | No goals | No subtasks
Kick off meeting Fase 2
15 Apr 2019 - 16 Apr 2019 (2 days) |  | No goals | No subtasks
Open Questions fase 2
17 Apr 2019 - 23 Apr 2019 (5 days) |  | No goals | No subtasks
Analysis data fase 2
24 Apr 2019 - 3 May 2019 (8 days) |  | No goals | No subtasks
Team meeting Fase 2
25 Apr 2019 - 26 Apr 2019 (2 days) |  | No goals | No subtasks
Plan a draft of your strategy Fase 2
29 Apr 2019 - 1 May 2019 (3 days) |  | No goals | No subtasks