## Gantt planification
Marketing Plan Template
Project Manager
2019-03-26 15:08
|  | March 2019 | [9 empty] | April 2019 | [21 empty] | May 2019 | [42 empty] | July 2019
 | time axis 2019-03-18 to 2019-07-12
Project activities | Status | time axis 2019-03-18 to 2019-07-12
Client Meeting 1 | doing ok | bar: 2019-03-20 to 2019-03-26
Survey | todo
External Analysis | todo | bar: 2019-04-10 to 2019-04-18
Survey Results Analysis | todo
Internal Analysis | todo | bar: 2019-04-19 to 2019-04-29
Estimated Goals | todo
Client Meeting 2 | todo | bar: 2019-04-30 to 2019-05-06
Define strategy | todo
Optimize Media Plan | todo | bar: 2019-05-07 to 2019-05-17
Budget and ROI | todo
Table for control indicators | todo | bar: 2019-05-23 to 2019-05-27
Client Meeting 3 | todo
Scenario Planning | todo | bar: 2019-05-28 to 2019-05-30
Materials development | todo | bar: 2019-03-18; 2019-03-20 to 2019-03-25; 2019-03-27 to 2019-05-30; 2019-06-18 to 2019-07-12
Conclusions | todo
Details and annexes | todo
Delivery | todo | bar: 2019-07-01 to 2019-07-02

## Project overview
Marketing Plan Template
2019-03-26 15:08
Project team | Role
User | Project owner
Activity | Involved | Goals |  | Subtasks | Assigned to | Date | Time
Client Meeting 1
20 Mar 2019 - 26 Mar 2019 (5 days) |  | No goals |  | No subtasks
Survey
27 Mar 2019 - 17 Apr 2019 (16 days) |  | No goals |  | No subtasks
External Analysis (0% Completed)
10 Apr 2019 - 18 Apr 2019 (7 days) |  | No goals | - | Market
|  |  | - | Competitors
|  |  | - | FODA
Survey Results Analysis
18 Apr 2019 - 1 May 2019 (10 days) |  | No goals |  | No subtasks
Internal Analysis (0% Completed)
19 Apr 2019 - 29 Apr 2019 (7 days) |  | No goals | - | Target
|  |  | - | Customer Journey
|  |  | - | Current Strategy
Estimated Goals
30 Apr 2019 - 1 May 2019 (2 days) |  | No goals |  | No subtasks
Client Meeting 2
30 Apr 2019 - 6 May 2019 (5 days) |  | No goals |  | No subtasks
Define strategy
2 May 2019 - 6 May 2019 (3 days) |  | No goals |  | No subtasks
Optimize Media Plan (0% Completed)
7 May 2019 - 17 May 2019 (9 days) |  | No goals | - | Define campaigns
|  |  | - | Rate research
Budget and ROI
20 May 2019 - 22 May 2019 (3 days) |  | No goals |  | No subtasks
Table for control indicators
23 May 2019 - 27 May 2019 (3 days) |  | No goals |  | No subtasks
Client Meeting 3
27 May 2019 - 31 May 2019 (5 days) |  | No goals |  | No subtasks
Scenario Planning
28 May 2019 - 30 May 2019 (3 days) |  | No goals |  | No subtasks
Materials development
31 May 2019 - 17 Jun 2019 (12 days) |  | No goals |  | No subtasks
Conclusions
18 Jun 2019 - 19 Jun 2019 (2 days) |  | No goals |  | No subtasks
Details and annexes
20 Jun 2019 - 21 Jun 2019 (2 days) |  | No goals |  | No subtasks
Delivery
1 Jul 2019 - 2 Jul 2019 (2 days) |  | No goals |  | No subtasks