## Gantt planification
Marketing Plan Template
Teresa Canive
2019-06-19 10:46
|  | June 2019 |  |  |  |  | July 2019 | [22 empty] | August 2019 | [21 empty] | September 2019 | [20 empty] | October 2019
 | time axis 2019-06-24 to 2019-10-11
Project activities | Status | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Client Meeting 1 | todo | bar: 2019-06-24 to 2019-06-28
External Analysis | todo
Survey | todo | bar: 2019-07-01 to 2019-07-22
Internal Analysis | todo
Survey Results Analysis | todo | bar: 2019-07-23 to 2019-08-02
Client Meeting 2 | todo
Estimated Goals | todo | bar: 2019-08-07 to 2019-08-08
Define strategy | todo
Optimize Media Plan | todo | bar: 2019-08-14 to 2019-08-26
Budget and ROI | todo
Table for control indicators | todo | bar: 2019-08-30 to 2019-09-03
Scenario Planning | todo
Client Meeting 3 | todo | bar: 2019-09-09 to 2019-09-10
Materials development | todo | bar: 2019-06-25 to 2019-09-10; 2019-09-27 to 2019-10-11
Delivery | todo | bar: 2019-09-27 to 2019-09-30

## Project overview
Marketing Plan Template
Teresa Canive
2019-06-19 10:46
Project team | Role
Teresa Canive (tere) | Project owner
Patricia Parra (patriprueba) | Team member
Activity | Involved | Goals |  | Subtasks | Assigned to | Date | Time
Client Meeting 1
24 Jun 2019 - 28 Jun 2019 (5 days) | Patricia Parra (patriprueba) | No goals |  | No subtasks
External Analysis (0% Completed)
1 Jul 2019 - 9 Jul 2019 (7 days) | Teresa Canive (tere) | No goals | - | Market
| Patricia Parra (patriprueba) |  | - | Competitors
|  |  | - | FODA
Survey
1 Jul 2019 - 22 Jul 2019 (16 days) | Teresa Canive (tere) | No goals |  | No subtasks
Patricia Parra (patriprueba)
Internal Analysis (0% Completed)
10 Jul 2019 - 22 Jul 2019 (9 days) | Patricia Parra (patriprueba) | No goals | - | Target
|  |  | - | Customer Journey
|  |  | - | Current Strategy
Survey Results Analysis
23 Jul 2019 - 2 Aug 2019 (9 days) | Teresa Canive (tere) | No goals |  | No subtasks
Client Meeting 2
5 Aug 2019 - 6 Aug 2019 (2 days) | Teresa Canive (tere) | No goals |  | No subtasks
Estimated Goals (0% Completed)
7 Aug 2019 - 8 Aug 2019 (2 days) | Patricia Parra (patriprueba) | No goals | - | Crear cuenta |  | 1 May 2019 | 01:00
Define strategy
9 Aug 2019 - 13 Aug 2019 (3 days) | Teresa Canive (tere) | No goals |  | No subtasks
Optimize Media Plan (50% Completed)
14 Aug 2019 - 26 Aug 2019 (9 days) | Teresa Canive (tere) | No goals | ✓ | Define campaigns
| Patricia Parra (patriprueba) |  | - | Rate research
Budget and ROI
27 Aug 2019 - 29 Aug 2019 (3 days) | Patricia Parra (patriprueba) | No goals |  | No subtasks
Table for control indicators
30 Aug 2019 - 3 Sep 2019 (3 days) | Patricia Parra (patriprueba) | No goals |  | No subtasks
Scenario Planning
4 Sep 2019 - 6 Sep 2019 (3 days) |  | No goals |  | No subtasks
Client Meeting 3
9 Sep 2019 - 10 Sep 2019 (2 days) |  | No goals |  | No subtasks
Materials development
11 Sep 2019 - 26 Sep 2019 (12 days) |  | No goals |  | No subtasks
Delivery
27 Sep 2019 - 30 Sep 2019 (2 days) |  | No goals |  | No subtasks