## Gantt planification
Product development
Teresa Canive
2019-06-21 16:22
|  | April 2019 |  | May 2019 | [22 empty] | June 2019 | [19 empty] | July 2019 | [22 empty] | August 2019
 | time axis 2019-04-29 to 2019-08-16
Project activities | Status | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Kick-Off | done
Convocatoria listado | done
Análisis de competidores | done | bar: 2019-05-01 to 2019-05-07
Planificación de proyecto | done
Introducción de proyecto | done
Acuerdo de planificación | done
Confirmar del brief | done
Estudio de mercado | done
Estudio de usabilidad | done
Estudio volumétrico | done
Maqueta volumétrica | done
Workshop de diseño | done
Revisión volumétrica | done
Workshop estético | done
Exploración dirección de diseño | done | bar: 2019-05-27 to 2019-05-29
Exploración materiales de diseño | done
Exploración de interfaz de usuario | done
Explorar Decoración 3D | done
Renderizar M&F | done | bar: 2019-05-30 to 2019-06-05
Implementación de familia de productos | done
Design Update | doing late
Revisión diseño | done
Design test | done
Design direction | doing ok
Marketing report | doing ok
Actividad 1 | doing late
Actividad 2 | doing ok
Color test | todo
Detailing | todo
Surface restoration | todo | bar: 2019-04-29; 2019-05-01 to 2019-06-20; 2019-06-24 to 2019-06-25; 2019-07-12 to 2019-08-16
User panel and family implementation | todo
Finishing up 02 | todo | bar: 2019-04-29; 2019-05-01 to 2019-06-20; 2019-06-24 to 2019-06-25; 2019-07-11 to 2019-08-16
Dirección de materiales y acabados | todo
Final testing and design direction | todo
Design finishing touches | todo | bar: 2019-07-04 to 2019-07-29
Workshop de proveedor | todo
UI refinada | todo
Maqueta prototipo | todo
Implementación acabados 3D | todo
Pruebas finales de usuario | todo
Revisión y validación final | todo | bar: 2019-07-29 to 2019-08-02

## Project overview
Product development
Teresa Canive
2019-06-21 16:22
Project team | Role
Richard Balet (richard) | Project owner
Diego Bergua (dbergua) | Project manager
Ricardo Monti (ricardo monti372) | Team member
Javier Alcubierre (javier.alcubierre) | Team member
Teresa Canive (tere) | Project manager
Activity | Involved |  | Goals |  | Subtasks | Assigned to | Date | Time
Kick-Off
30 Apr 2019 - 30 Apr 2019 (1 days) |  |  | No goals |  | No subtasks
Convocatoria listado
30 Apr 2019 - 6 May 2019 (5 days) |  |  | No goals |  | No subtasks
Análisis de competidores
1 May 2019 - 7 May 2019 (5 days) | Richard Balet (richard) |  | No goals |  | No subtasks
Planificación de proyecto
1 May 2019 - 3 May 2019 (3 days) |  |  | No goals |  | No subtasks
Introducción de proyecto
1 May 2019 - 1 May 2019 (1 days) |  |  | No goals |  | No subtasks
Acuerdo de planificación
6 May 2019 - 6 May 2019 (1 days) |  |  | No goals |  | No subtasks
Confirmar del brief
8 May 2019 - 8 May 2019 (1 days) |  |  | No goals |  | No subtasks
Estudio de mercado (100% Completed)
8 May 2019 - 10 May 2019 (3 days) | Richard Balet (richard) |  | No goals | ✓ | wefwefewf
Estudio de usabilidad
9 May 2019 - 15 May 2019 (5 days) |  |  | No goals |  | No subtasks
Estudio volumétrico
9 May 2019 - 15 May 2019 (5 days) | Richard Balet (richard) |  | No goals |  | No subtasks
Maqueta volumétrica
16 May 2019 - 20 May 2019 (3 days) |  |  | No goals |  | No subtasks
Workshop de diseño
16 May 2019 - 17 May 2019 (2 days) |  |  | No goals |  | No subtasks
Revisión volumétrica
21 May 2019 - 22 May 2019 (2 days) |  |  | No goals |  | No subtasks
Workshop estético
23 May 2019 - 24 May 2019 (2 days) |  |  | No goals |  | No subtasks
Exploración dirección de diseño (0% Completed)
27 May 2019 - 29 May 2019 (3 days) |  |  | No goals | - | comparar el pan
Exploración materiales de diseño
27 May 2019 - 28 May 2019 (2 days) |  |  | No goals |  | No subtasks
Exploración de interfaz de usuario
27 May 2019 - 31 May 2019 (5 days) | Richard Balet (richard) |  | No goals |  | No subtasks
Explorar Decoración 3D (50% Completed)
30 May 2019 - 7 Jun 2019 (7 days) | Diego Bergua (dbergua) |  | No goals | ✓ | Prepare docs
| Richard Balet (richard) |  |  | - | Check resources
Renderizar M&F
30 May 2019 - 5 Jun 2019 (5 days) |  |  | No goals |  | No subtasks
Implementación de familia de productos
6 Jun 2019 - 12 Jun 2019 (5 days) |  |  | No goals |  | No subtasks
Design Update (80% Completed)
10 Jun 2019 - 17 Jun 2019 (6 days) | Javier Alcubierre (javier.alcubierre) | ✓ | Certificación | ✓ | Subtareas
| Diego Bergua (dbergua) |  |  | ✓ | Informe de compra
| Richard Balet (richard) |  |  | ✓ | Informe de resolución
|  |  |  | ✓ | Validación de management | Javier Alcubierre
|  |  |  | - | Test calidad A/B | Richard Balet
Revisión diseño
10 Jun 2019 - 10 Jun 2019 (1 days) |  |  | No goals |  | No subtasks
Design test (50% Completed)
11 Jun 2019 - 14 Jun 2019 (4 days) | Richard Balet (richard) |  | No goals | ✓ | sUBTAREA
|  |  |  | - | Iforme
Design direction (66% Completed)
18 Jun 2019 - 25 Jun 2019 (6 days) | Diego Bergua (dbergua) |  | No goals | ✓ | Benchmarking | Richard Balet
| Richard Balet (richard) |  |  | ✓ | Develop other alternatives | Richard Balet
|  |  |  | - | Sketches and designs
|  |  |  | ✓ | Marketing study
|  |  |  | ✓ | Finish report | Diego Bergua | 29 Nov 2018
|  |  |  | - | Realizar un informe | Diego Bergua
Marketing report (75% Completed)
18 Jun 2019 - 21 Jun 2019 (4 days) | Diego Bergua (dbergua) | ✓ | Entrega de informe | ✓ | Define Scope | Diego Bergua
| Richard Balet (richard) | ✓ | Conseguir certificación | ✓ | Define target | Richard Balet |  | 00:30
|  | - | Adjuntar facturas | ✓ | Testing | Diego Bergua
|  |  |  | - | Benchmarking
Actividad 1
20 Jun 2019 - 20 Jun 2019 (1 days) |  |  | No goals |  | No subtasks
Actividad 2
21 Jun 2019 - 21 Jun 2019 (1 days) |  |  | No goals |  | No subtasks
Color test (0% Completed)
26 Jun 2019 - 28 Jun 2019 (3 days) | Richard Balet (richard) |  | No goals | - | sasasasas
|  |  |  | - | ddasd
Detailing (40% Completed)
26 Jun 2019 - 3 Jul 2019 (6 days) | Diego Bergua (dbergua) | ✓ | Nuevo objetivo | ✓ | Subtarea 01
| Richard Balet (richard) |  |  | ✓ | Subtarea 01
|  |  |  | - | Subtarea 01
|  |  |  | - | Subtarea 01
|  |  |  | - | Subtarea 01 |  | 27 Dec 2018
Surface restoration
26 Jun 2019 - 11 Jul 2019 (12 days) |  |  | No goals |  | No subtasks
User panel and family implementation (28% Completed)
26 Jun 2019 - 15 Jul 2019 (14 days) | Diego Bergua (dbergua) |  | No goals | ✓ | Subtarea 01
| Richard Balet (richard) |  |  | - | Subtarea 01
|  |  |  | - | Subtarea 01
|  |  |  | - | Subtarea 01
|  |  |  | ✓ | Subtarea 01
|  |  |  | - | Subtarea 01
|  |  |  | - | Subtarea 01
Finishing up 02 (25% Completed)
26 Jun 2019 - 10 Jul 2019 (11 days) | Diego Bergua (dbergua) |  | No goals | ✓ | Subtarea 01
|  |  |  | - | Subtarea 01
|  |  |  | ✓ | Subtarea 01Subtarea 01
|  |  |  | - | Subtarea 01Subtarea 01
|  |  |  | - | Subtarea 01Subtarea 01
|  |  |  | - | Subtarea 01Subtarea 01
|  |  |  | - | Subtarea 01
|  |  |  | - | Subtarea 01
Dirección de materiales y acabados
26 Jun 2019 - 12 Jul 2019 (13 days) |  |  | No goals |  | No subtasks
Final testing and design direction
1 Jul 2019 - 12 Jul 2019 (10 days) | Diego Bergua (dbergua) |  | No goals |  | No subtasks
Design finishing touches
4 Jul 2019 - 29 Jul 2019 (18 days) |  |  | No goals |  | No subtasks
Workshop de proveedor (0% Completed)
12 Jul 2019 - 18 Jul 2019 (5 days) | Richard Balet (richard) |  | No goals | - | Subtarea 01
|  |  |  | - | Subtarea 02
|  |  |  | - | Subtarea 03
|  |  |  | - | Subtarea 04
UI refinada
12 Jul 2019 - 18 Jul 2019 (5 days) | Diego Bergua (dbergua) |  | No goals |  | No subtasks
Richard Balet (richard)
Maqueta prototipo
15 Jul 2019 - 22 Jul 2019 (6 days) | Richard Balet (richard) |  | No goals |  | No subtasks
Implementación acabados 3D
19 Jul 2019 - 23 Jul 2019 (3 days) | Diego Bergua (dbergua) |  | No goals |  | No subtasks
Pruebas finales de usuario
23 Jul 2019 - 26 Jul 2019 (4 days) | Richard Balet (richard) |  | No goals |  | No subtasks
Revisión y validación final (100% Completed)
29 Jul 2019 - 2 Aug 2019 (5 days) | Diego Bergua (dbergua) |  | No goals | ✓ | test
| Richard Balet (richard) |  |  | ✓ | Subtasks