## Gantt planification
Content Marketing Plan
Teresa Canive
2019-07-12 12:22
|  | July 2019 | [22 empty] | August 2019 | [21 empty] | September 2019 | [20 empty] | October 2019
 | time axis 2019-07-01 to 2019-10-04
Project activities | Status | time axis 2019-07-01 to 2019-10-04
Market Research | todo | bar: 2019-07-18 to 2019-07-24
Analysis of Direct Competition | todo
Meeting - Target | todo | bar: 2019-08-01 to 2019-08-02
Design Objetives | todo
Design Social Strategy | todo | bar: 2019-08-09 to 2019-08-15
Design Channels | todo
PR Strategy | todo | bar: 2019-08-09 to 2019-08-15
Design Content | todo
Meeting 2 | todo | bar: 2019-08-16 to 2019-08-20
Content | todo
Webinars | todo | bar: 2019-08-21 to 2019-09-09
Ebook | todo
Email MK automations | todo | bar: 2019-09-10 to 2019-09-16
Social Media automations | todo
Meeting - Presentation | todo | bar: 2019-09-17 to 2019-09-19
Meeting - Design KPIs | todo

## Project overview
Content Marketing Plan
Teresa Canive
2019-07-12 12:22
Project team | Role
Teresa Canive (tere) | Project owner
Activity | Involved | Goals | Subtasks | Assigned to | Date | Time
Market Research
18 Jul 2019 - 24 Jul 2019 (5 days) |  | No goals | No subtasks
Analysis of Direct Competition
25 Jul 2019 - 31 Jul 2019 (5 days) |  | No goals | No subtasks
Meeting - Target
1 Aug 2019 - 2 Aug 2019 (2 days) |  | No goals | No subtasks
Design Objetives
5 Aug 2019 - 8 Aug 2019 (4 days) |  | No goals | No subtasks
Design Social Strategy
9 Aug 2019 - 15 Aug 2019 (5 days) |  | No goals | No subtasks
Design Channels
9 Aug 2019 - 15 Aug 2019 (5 days) |  | No goals | No subtasks
PR Strategy
9 Aug 2019 - 15 Aug 2019 (5 days) |  | No goals | No subtasks
Design Content
9 Aug 2019 - 15 Aug 2019 (5 days) |  | No goals | No subtasks
Meeting 2
16 Aug 2019 - 20 Aug 2019 (3 days) |  | No goals | No subtasks
Content
21 Aug 2019 - 9 Sep 2019 (14 days) |  | No goals | No subtasks
Webinars
21 Aug 2019 - 9 Sep 2019 (14 days) |  | No goals | No subtasks
Ebook
21 Aug 2019 - 9 Sep 2019 (14 days) |  | No goals | No subtasks
Email MK automations
10 Sep 2019 - 16 Sep 2019 (5 days) |  | No goals | No subtasks
Social Media automations
10 Sep 2019 - 16 Sep 2019 (5 days) |  | No goals | No subtasks
Meeting - Presentation
17 Sep 2019 - 19 Sep 2019 (3 days) |  | No goals | No subtasks
Meeting - Design KPIs
20 Sep 2019 - 26 Sep 2019 (5 days) |  | No goals | No subtasks