## Gantt planification
Marketing Plan
Teresa Cam
2019-09-20 12:31
|  | September 2019 | [28 empty] | October 2019 | October 2019 | [29 empty] | November 2019
 | time axis 2019-09-02 to 2019-11-10
Project activities | Status | time axis 2019-09-02 to 2019-11-10
Meeting | doing late
Congress | doing late
Presentation for the team | doing late
Delivery | doing late
EnterviewS28 | done
Finish agency proposal | doing late
Analysis of Direct Competition | done
Market Research | doing late
Presentation 2 | doing late | bar: 2019-09-08 to 2019-09-12
Agency | done
Report Design | done | bar: 2019-09-08 to 2019-09-13
Congress 2 | doing late
Design Objetives | doing ok | bar: 2019-09-20 to 2019-09-24
Design Context | todo
Analysis of indirect competition | todo
Presentation | todo
Design Social Strategy | todo | bar: 2019-09-29 to 2019-10-03
Target | todo
Meeting2 | todo
Backlog | todo
Proposal Draft | todo
Delivery 1 | todo
Management | todo | bar: 2019-10-18 to 2019-10-22
Presentation 3 | todo
PR contact | todo | bar: 2019-10-18 to 2019-10-22
Designs | todo
Proposal | todo
Design review | todo
Meeting 3 | todo

## Project overview
Marketing Plan
Teresa Cam
2019-09-20 12:31
Project team | Role
Teresa Cam | Project owner
Richard Balet | Project manager
Diego Bergua | Team member
Patricia Parra Mateos | Team member
Activity | Involved |  | Goals |  | Subtasks | Assigned to | Date | Time
Meeting
2 Sep 2019 - 2 Sep 2019 (1 days) |  |  | No goals |  | No subtasks
Congress
2 Sep 2019 - 2 Sep 2019 (1 days) |  |  | No goals |  | No subtasks
Presentation for the team (50% Completed)
2 Sep 2019 - 2 Sep 2019 (1 days) |  |  | No goals | ✓ | Ppt
|  |  |  | - | Communication
Delivery (100% Completed)
2 Sep 2019 - 3 Sep 2019 (2 days) |  |  | No goals | ✓ | bcvbcv
|  |  |  | ✓ | kjhkjhbj
|  |  |  | ✓ | vblhxck
EnterviewS28
3 Sep 2019 - 7 Sep 2019 (5 days) | Teresa Cam (teresacam) |  | No goals |  | No subtasks
Finish agency proposal
3 Sep 2019 - 7 Sep 2019 (5 days) | Richard Balet |  | No goals |  | No subtasks
Teresa Cam (teresacam)
Analysis of Direct Competition
3 Sep 2019 - 7 Sep 2019 (5 days) | Teresa Cam (teresacam) |  | No goals |  | No subtasks
Market Research
8 Sep 2019 - 19 Sep 2019 (12 days) |  |  | No goals |  | No subtasks
Presentation 2
8 Sep 2019 - 12 Sep 2019 (5 days) | Teresa Cam (teresacam) |  | No goals |  | No subtasks
Agency
8 Sep 2019 - 14 Sep 2019 (7 days) | Richard Balet | - | PR Agency |  | No subtasks
Teresa Cam (teresacam)
Report Design (33% Completed)
8 Sep 2019 - 13 Sep 2019 (6 days) | Richard Balet |  | No goals | ✓ | Draft | Richard Balet
| Teresa Cam (teresacam) |  |  | - | Subtask 02 | Teresa Cam
|  |  |  | - | Subtask 03 |  | 30 Aug 2018 | 10:00
Congress 2
13 Sep 2019 - 17 Sep 2019 (5 days) |  |  | No goals |  | No subtasks
Design Objetives (20% Completed)
20 Sep 2019 - 24 Sep 2019 (5 days) | Diego Bergua | ✓ | Review the plan | ✓ | Determine the | Richard Balet
| Richard Balet | - | Analysis of data | - | Determine the subjec | Diego Bergua
|  |  |  | - | Meeting | Richard Balet | 13 Jan 2018 | 01:00
|  |  |  | - | Draft | Teresa Cam
|  |  |  | - | hi | Richard Balet
Design Context (100% Completed)
25 Sep 2019 - 28 Sep 2019 (4 days) | Teresa Cam (teresacam) | - | Test 01 | ✓ | Analysis 1
|  | - | Overview | ✓ | Success Case
|  | ✓ | First Draft | ✓ | Subtask |  | 4 Jan 2018 | 01:30
|  |  |  | ✓ | Analysis 2 | Teresa Cam |  | 02:00
|  |  |  | ✓ | Suppliers | Teresa Cam | 16 Jan 2018
Analysis of indirect competition (0% Completed)
25 Sep 2019 - 26 Sep 2019 (2 days) |  |  | No goals | - | Drafts
Presentation
29 Sep 2019 - 29 Sep 2019 (1 days) |  | ✓ | Results test |  | No subtasks
|  | - | Make a decision
Design Social Strategy
29 Sep 2019 - 3 Oct 2019 (5 days) | Richard Balet |  | No goals |  | No subtasks
Target
30 Sep 2019 - 1 Oct 2019 (2 days) |  |  | No goals |  | No subtasks
Meeting2
30 Sep 2019 - 1 Oct 2019 (2 days) |  |  | No goals |  | No subtasks
Backlog
16 Oct 2019 - 17 Oct 2019 (2 days) |  |  | No goals |  | No subtasks
Proposal Draft
18 Oct 2019 - 22 Oct 2019 (5 days) | Diego Bergua |  | No goals |  | No subtasks
Richard Balet
Teresa Cam (teresacam)
Delivery 1
18 Oct 2019 - 25 Oct 2019 (8 days) | Diego Bergua |  | No goals |  | No subtasks
Richard Balet
Teresa Cam (teresacam)
Management
18 Oct 2019 - 22 Oct 2019 (5 days) | Richard Balet |  | No goals |  | No subtasks
Teresa Cam (teresacam)
Presentation 3
18 Oct 2019 - 22 Oct 2019 (5 days) | Teresa Cam (teresacam) |  | No goals |  | No subtasks
PR contact
18 Oct 2019 - 22 Oct 2019 (5 days) |  |  | No goals |  | No subtasks
Designs
18 Oct 2019 - 20 Oct 2019 (3 days) |  |  | No goals |  | No subtasks
Proposal
18 Oct 2019 - 19 Oct 2019 (2 days) |  |  | No goals |  | No subtasks
Design review
23 Oct 2019 - 31 Oct 2019 (9 days) | Diego Bergua |  | No goals |  | No subtasks
Richard Balet
Meeting 3
23 Oct 2019 - 24 Oct 2019 (2 days) |  |  | No goals |  | No subtasks