## Gantt planification
Marketing Plan Template
Teresa Canive
2020-04-07 14:27
|  | April 2020 | [18 empty] | May 2020 | [20 empty] | June 2020
 | time axis 2020-04-06 to 2020-06-05
Project activities | Status | time axis 2020-04-06 to 2020-06-05
External Analysis | done | bar: 2020-04-06 to 2020-04-08
Internal Analysis | todo
Survey | todo | bar: 2020-04-09 to 2020-04-16
Client Meeting 1 | done
Client Meeting 2 | todo | bar: 2020-04-16 to 2020-04-17
Survey Results Analysis | todo
Estimated Goals | todo | bar: 2020-04-20 to 2020-04-21
Define strategy | todo
Optimize Media Plan | todo | bar: 2020-04-27 to 2020-04-29
Budget and ROI | todo
Table for control indicators | todo | bar: 2020-05-05 to 2020-05-07
Scenario Planning | todo
Client Meeting 3 | todo | bar: 2020-05-13 to 2020-05-14
Materials development | todo | bar: 2020-04-08 to 2020-05-14; 2020-05-22 to 2020-06-05
Delivery | todo | bar: 2020-05-22 to 2020-05-25

## Project overview
Marketing Plan Template
Teresa Canive
2020-04-07 14:27
Project team | Role
Teresa Canive | Project owner
Patricia Parra | Team member
Jonas Jonas | Team member
Activity | Involved | Goals |  | Subtasks | Assigned to | Date | Time
External Analysis (66% Completed)
6 Apr 2020 - 8 Apr 2020 (3 days) | Teresa Canive | No goals | - | Market
| Patricia Parra |  | ✓ | Competitors
|  |  | ✓ | FODA
Internal Analysis (0% Completed)
9 Apr 2020 - 13 Apr 2020 (3 days) | Jonas Jonas (jonasjj) | No goals | - | Target
| Patricia Parra |  | - | Customer Journey
|  |  | - | Current Strategy
Survey
9 Apr 2020 - 16 Apr 2020 (6 days) | Teresa Canive | No goals |  | No subtasks
Patricia Parra
Client Meeting 1
14 Apr 2020 - 15 Apr 2020 (2 days) | Patricia Parra | No goals |  | No subtasks
Client Meeting 2
16 Apr 2020 - 17 Apr 2020 (2 days) | Teresa Canive | No goals |  | No subtasks
Survey Results Analysis
17 Apr 2020 - 29 Apr 2020 (9 days) | Teresa Canive | No goals |  | No subtasks
Estimated Goals (0% Completed)
20 Apr 2020 - 21 Apr 2020 (2 days) | Patricia Parra | No goals | - | Crear cuenta |  | 1 May 2019 | 01:00
Define strategy
22 Apr 2020 - 24 Apr 2020 (3 days) | Teresa Canive | No goals |  | No subtasks
Optimize Media Plan (50% Completed)
27 Apr 2020 - 29 Apr 2020 (3 days) | Teresa Canive | No goals | ✓ | Define campaigns
| Patricia Parra |  | - | Rate research
Budget and ROI
30 Apr 2020 - 4 May 2020 (3 days) | Patricia Parra | No goals |  | No subtasks
Table for control indicators
5 May 2020 - 7 May 2020 (3 days) | Patricia Parra | No goals |  | No subtasks
Scenario Planning
8 May 2020 - 12 May 2020 (3 days) |  | No goals |  | No subtasks
Client Meeting 3
13 May 2020 - 14 May 2020 (2 days) |  | No goals |  | No subtasks
Materials development
15 May 2020 - 21 May 2020 (5 days) |  | No goals |  | No subtasks
Delivery
22 May 2020 - 25 May 2020 (2 days) |  | No goals |  | No subtasks